## Project Timeline
ePublication System Upgrade & Enhancement Project
Implementation Roadmap & Detailed Schedule ¦ Umbraco 8 to Umbraco 17 Migration
TARGET GO-LIVE |  | CORE MIGRATION |  | UAT WINDOW |  | PROJECT WINDOW
05-06 Dec 2026 |  | Umbraco 8 → 17 |  | 16 Nov - 25 Nov 2026 |  | 21 Sep - 15 Dec 2026
Phase | Activity / Key Deliverables | Owner | Start Date | End Date | Working Days | Key Output & Milestone Objective
Phase 1: Planning & Setup | Project kickoff, environment readiness, DEV/SIT setup, and baseline DB & media assets backup | ITD | 2026-09-21 | 2026-09-25 | 5 | Staging environments prepared; baseline DB secured
Phase 2: Database Housekeeping | Convert historical manual versions to standalone HTML, establish URL mappings, and purge obsolete version records from CMS DB | ITD | 2026-09-28 | 2026-10-09 | 10 | Cleaned database; archived HTML manuals accessible; DB size reduced
Phase 3: Core Upgrade & Migration (Umbraco 8 → 17) | Major framework migration (.NET Framework to modern .NET), DB schema upgrade, API/namespace updates, on-demand cache configuration, and backend engine refactoring | ITD | 2026-10-12 | 2026-10-30 | 15 | Stable Umbraco 17 core running on DEV/SIT; on-demand cache active
Phase 4: Enhancements Integration | Port, merge, and integrate the deferred enhancements from the failed deployment into the new Umbraco 17 codebase | ITD | 2026-11-02 | 2026-11-06 | 5 | Complete unified build (Upgrade + Enhancements ready)
Phase 5: Internal Testing & SIT | System Integration Testing, cache performance benchmarking, and application restart load stress testing | ITD | 2026-11-09 | 2026-11-13 | 5 | SIT Sign-off; verified fix for DB locking and system hang
Phase 6: User Acceptance Testing (UAT) | Business user verification of content editing, manual publishing, HTML archives, and new enhancements | EMQC | 2026-11-16 | 2026-11-25 | 8 | Formal Business UAT Sign-off
Phase 7: Web Security Assessment | Web Application Assessment / VAPT scan on UAT-validated candidate build, vulnerability triage, and security patch remediation | ITD | 2026-11-26 | 2026-12-02 | 5 | VAPT clearance & clean security remediation closure report
Phase 8: Cutover Readiness & Rehearsal | Staging dry-run, rollback drill, finalize production runbook, and user communication notices | ITD | 2026-12-03 | 2026-12-04 | 2 | Production cutover plan approved & rehearsal completed
Phase 9: Production Deployment | Scheduled production cutover window: Umbraco 17 migration, HTML archives cutover, and deployment of enhancements | ITD | 2026-12-05 | 2026-12-06 | 0 | System successfully live in Production (Early December)
Phase 10: Hypercare & Support | Post-deployment hypercare monitoring, performance observation, and priority issue resolution | ITD | 2026-12-07 | 2026-12-15 | 7 | Operational stabilization & formal project handover
Formulas:
Working Days = NETWORKDAYS([Start Date],[UAT WINDOW])

## Executive Milestones
Executive Milestone Tracker
High-Level Milestone Gates for Stakeholders & Management
Milestone # | Key Gate / Deliverable | Target Date | Responsible Party | Success Criteria
M1 | Version Manuals Mapping to HTML & DB Cleaned | 2026-10-09 | ITD | DB purged of heavy versions; standalone HTML verified accessible
M2 | Umbraco 8 → 17 Migration & Engine Refactoring Completed | 2026-10-30 | ITD | Clean build on modern .NET with on-demand cache operational
M3 | Unified Build Ready (Enhancements Merged & SIT Passed) | 2026-11-13 | ITD | Zero critical defects; no cache-rebuild freeze during restart
M4 | Business User Acceptance Testing (UAT) Sign-off | 2026-11-25 | EMQC | Formal business sign-off
M5 | Web Security Assessment (VAPT) Cleared | 2026-12-02 | ITD | All High/Medium vulnerabilities remediated and signed off
M6 | Production Go-Live & Cutover | 2026-12-06 | ITD | Successful weekend cutover with system accessible in Production